## Summary
| Total |  |  |  | Coding |  |  |  | Meetings |  |  |  | Systems Analysis |  |  |  | Overhead
| Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit
Alex | 1500 | 2100 |  | Alex |  |  |  | Alex |  |  |  | Alex | 1500 | 2100 | 600 | Alex
Todd | 2000 | 3000 |  | Todd |  |  |  | Todd |  |  |  | Todd | 2000 | 3000 | 1000 | Todd
Liz | 900 | 2250 |  | Liz |  |  |  | Liz |  |  |  | Liz | 900 | 2250 | 1350 | Liz
Shan | 1800 | 0 |  | Shan |  |  |  | Shan |  |  |  | Shan | 1800 |  |  | Shan
Hengyi | 1750 | 2650 |  | Hengyi |  |  |  | Hengyi |  |  |  | Hengyi | 1750 | 2650 | 900 | Hengyi
Mark | 1250 | 0 |  | Mark |  |  |  | Mark |  |  |  | Mark | 1250 |  |  | Mark
Bidhan | 700 | 1300 |  | Bidhan |  |  |  | Bidhan |  |  |  | Bidhan | 700 | 1300 | 600 | Bidhan
Total |  |  |  | Total |  |  |  | Total |  |  |  | Total | 9900 |  |  | Total

## Gantt
Gantt Chart
|  | Task | Status | Predicted (hrs) | Time Spent (hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
Alex | 1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150

## SA
Systems Analysis Chart
|  | Task | Status | Predicted (hrs) | Time Spent (hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
Alex | 1 | Install Unity | Done | 1 | 2 | bar: 1 to 2
| 2 | Update RFP to Version 3.0 | Done | 1 | 2 | bar: 3 to 4
| 3 | Class Diagram | Done | 6 | 5 | bar: 5 to 9
| 4 | Champion | Done | 5 | 10 | bar: 10 to 19
| 5 | Sequence Diagram | Done | 2 | 2 | bar: 20 to 21
| 6 | Total |  | 15 | 21
7
Todd | 8 | Install Unity | Done | 1 | 1 | bar: 1
| 9 | Make Version 1.0 of RFP | Done | 1 | 1 | bar: 2
| 10 | Update RFP to Version 2.0 | Done | 1 | 1 | bar: 3
| 11 | Champion | Done | 8 | 15 | bar: 4 to 18
| 12 | Class Diagram | Done | 2 | 3 | bar: 19 to 21
| 13 | Diagram 0 | Done | 4 | 5 | bar: 22 to 26
| 14 | Class Diagram v2 | Done | 1 | 2 | bar: 27 to 28
| 15 | Sequence Diagram | Done | 2 | 2 | bar: 29 to 30
| 16 | Total |  | 20 | 30
17
Liz | 18 | Install Unity | Done | 1 | 1.5 | bar: 1 to 2
| 19 | Update RFP to Version 5.0 | Done | 2 | 1 | bar: 3
| 20 | Class Diagram | Done | 3 | 10 | bar: 4 to 13
| 21 | Champion | Done | 2 | 6 | bar: 14 to 19
| 22 | Sequence Diagram | Done | 1 | 4 | bar: 20 to 23
| 23 | Total |  | 9 | 22.5
24
Shan | 25 | Install Unity | Done | 2 | 1.5 | bar: 1 to 2
| 26 | Class Diagram v1 | Done | 3 | 3 | bar: 4 to 6
| 27 | Update RFP | Done | 2 | 1 | bar: 7
| 28 | Champion | Done | 7 | 13 | bar: 8 to 20
| 29 | Class Diagram v2 | Done | 1 | 4 | bar: 21 to 24
| 30 | Sequence Diagram | Done | 1 | 1 | bar: 25
| 31 | Create Schedule Charts | In Progress | 2 | 3 | bar: 3; 26 to 27
| 32 | Total |  | 18 | 26.5
33
Hengyi | 34 | Install Unity | Done | 1 | 1.5 | bar: 1 to 2
| 35 | Update RFP to Version 4.0 | Done | 2 | 3 | bar: 3 to 5
| 36 | Class Diagram v1 | Done | 1 | 2 | bar: 6 to 7
| 37 | Class Diagram v2 | Done | 2 | 2 | bar: 8 to 9
| 38 | Champion | Done | 10 | 16 | bar: 10 to 25
| 39 | Sequence Diagram | Done | 1.5 | 2 | bar: 26 to 27
| 40 | Total |  | 17.5 | 26.5
41
Mark | 42 | Install Unity | Done | 1 | 2 | bar: 1 to 2
| 43 | Class Diagram v1 | Done | 3 | 1 | bar: 3
| 44 | Class Diagram v2 | In Progress | 1
| 45 | Champion v1 | Done | 5 | 10 | bar: 4 to 13
| 46 | Champion v2 | In Progress | 0.5
| 47 | Sequence Diagram | Done | 2 | 1 | bar: 14
| 48 | Total |  | 12.5 | 14
49
Bidhan | 50 | Install Unity | Done | 1 | 2 | bar: 1 to 2
| 51 | Class Diagram | Done | 3 | 6 | bar: 3 to 8
| 52 | Champion | Done | 2 | 4 | bar: 9 to 12
| 53 | Sequence Diagram | Done | 1 | 1 | bar: 13
| 54 | Total |  | 7 | 13
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70

## Meetings
Team Meetings
| Date | 2025-02-05 | 2025-02-07 | 2025-02-12 | 2025-02-14 | 2025-02-17 | 2025-02-19
|  | Diagram 0 and Champion Discussion | Class Diagram Reviewing w/BC | SA Presentation Planning | Champion and Storyboard Reviewing w/BC | SA Pres Review w/BC | MVP Discussion
| Hours | 2 | 2.5 | 1.5 | 1.5 | 0.5 | 1.5
Alex | 9 | TRUE | TRUE | TRUE | TRUE |  | TRUE
Todd | 9.5 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Liz | 9.5 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Shan | 9 | TRUE | TRUE | TRUE | TRUE |  | TRUE
Hengyi | 8.5 | TRUE | TRUE | TRUE | 0.5 | TRUE | TRUE
Mark | 5.5 | TRUE |  | TRUE | 0.5 |  | TRUE
Bidhan | 5.5 | 2025-02-07: TRUE; 2025-02-12: TRUE; 2025-02-19: TRUE
Total | 56.5

## Overhead
| Alex | Todd | Liz | Shan | Hengyi | Mark | Bidhan
SA Presentation Prep | 5 | 6 | 2 | 2 | 8 | 7 | 5
Software Development Specialists Presentation Prep
Team Lead Presentation Prep | 10 | 15 |  | 2