## Summary
| Total |  |  |  | Coding |  |  |  | Meetings |  |  |  | Systems Analysis |  |  |  | Overhead
| Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit
Bidhan | 7300 | 4900 | 2400 | Bidhan | 2600 | 1600 | 1000 | Bidhan | 1000 | 700 | 300 | Bidhan | 700 | 1300 | -600 | Bidhan | 3000 | 1300 | 1700
Todd | 12200 | 10600 | 1600 | Todd | 6200 | 3500 | 2700 | Todd | 1000 | 1200 | -200 | Todd | 2000 | 3000 | -1000 | Todd | 3000 | 2900 | 100
Alex | 11400 | 9300 | 2100 | Alex | 5900 | 3400 | 2500 | Alex | 1000 | 1100 | -100 | Alex | 1500 | 2100 | -600 | Alex | 3000 | 2700 | 300
Mark | 11100 | 4600 | 6500 | Mark | 5800 | 1000 | 4800 | Mark | 1000 | 700 | 300 | Mark | 1300 | 1400 | -100 | Mark | 3000 | 1500 | 1500
Shan | 11600 | 6000 | 5600 | Shan | 5800 | 700 | 5100 | Shan | 1000 | 1100 | -100 | Shan | 1800 | 2900 | -1100 | Shan | 3000 | 1300 | 1700
Liz | 8100 | 6400 | 1700 | Liz | 3200 | 1900 | 1300 | Liz | 1000 | 1200 | -200 | Liz | 900 | 2300 | -1400 | Liz | 3000 | 1000 | 2000
Hengyi | 10900 | 7400 | 3500 | Hengyi | 5100 | 2100 | 3000 | Hengyi | 1000 | 1000 | 0 | Hengyi | 1800 | 2700 | -900 | Hengyi | 3000 | 1600 | 1400
Total | 72600 | 49200 | 23400 | Total | 34600 | 14200 | 20400 | Total | 7000 | 7000 | 0 | Total | 10000 | 15700 | -5700 | Total | 21000 | 12300 | 8700

## Gantt
Gantt Chart
|  | Task | Status | Predicted (hrs) | Time Spent (hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
Bidhan | 1 | Define Save System Requirements | Done | 2 | 2 | bar: 1 to 2
| 2 | Design Data Flow Diagrams | Done | 3 | 2 | bar: 3 to 4
| 3 | Implement Save Logic | Done | 4 | 6 | bar: 5 to 10
| 4 | Implement Load Logic | Done | 4 | 6 | bar: 11 to 16
| 5 | Create Data Storage Schema | Planned | 3
| 6 | Testing Save Functionality | Planned | 3
| 7 | Testing Load Functionality | Planned | 2
| 8 | Integration and System Testing | Planned | 2
| 9 | Deployment | Planned | 1
| 10 | User Documentation and Training | Planned | 2
| 11 | Total |  | 26 | 16
Todd | 12 | Requirements | Done | 3 | 3 | bar: 1 to 3
| 13 | Program NPC Manager | Done | 5 | 6 | bar: 4 to 9
| 14 | Program Game Object Manager | Done | 2 | 4 | bar: 10 to 13
| 15 | Program NPCs superclass | Done | 2 | 4 | bar: 14 to 17
| 16 | Program NPC dialogue system | Done | 10 | 10 | bar: 18 to 27
| 17 | Programming NPC combat response | In Progress | 10 | 8 | bar: 28 to 35
| 18 | Programming NPC dialogue for The Wolf | Planned | 2
| 19 | Programming NPC dialogue for The Bear | Planned | 2
| 20 | Programming NPC dialogue for The Hunter | Planned | 2
| 21 | Programming NPC dialogue for The Hiker | Planned | 2
| 22 | Programming NPC dialogue for The Wizard | Planned | 2
| 23 | Programming NPC dialogue for The Hippie | Planned | 2
| 24 | Programming NPC dialogue for The Axman | Planned | 2
| 25 | Programming NPC dialogue for The Cat | Planned | 2
| 26 | Programming NPC dialogue for The Owl | Planned | 2
| 27 | Programming NPC dialogue for The Fish | Planned | 2
| 28 | Testing | Planned | 10
| 29 | Total |  | 62 | 35
Alex | 30 | Determine requirements and constraints for levels and movement | Done | 3 | 2 | bar: 1 to 2
| 31 | Program levelMap and terrainObjects Classes and Scene Manager Script | Done | 5 | 9 | bar: 3 to 11
| 32 | Programming environmental objects that are stagnant but may cause damage or impede player movement | Done | 1 | 2 | bar: 12 to 13
| 33 | Programming a movable player object that interacts with environmental objects | Done | 8 | 2 | bar: 14 to 15
| 34 | Programming moving platforms between terrain areas on the same level | In Progress | 2 | 3 | bar: 16 to 18
| 35 | Programming death event for falling off the map or impacting deadly environmental objects | In Progress | 2 | 2 | bar: 19 to 20
| 36 | Programming passageways for additional levels or map areas | In Progress | 5 | 3 | bar: 21 to 23
| 37 | Programming locked passageways hiding and preventing movement through passageways | In Progress | 3 | 1 | bar: 24
| 38 | Programming and initializing Level 1 | In Progress | 4 | 10 | bar: 25 to 34
| 39 | Programming and initializing Level 2 | Planned | 4
| 40 | Programming and initializing Level 3 | Planned | 4
| 41 | Programming and initializing Level 4 | Planned | 4
| 42 | Programming and initializing Level 5 | Planned | 4
| 43 | Testing | Planned | 10
| 44 | Total |  | 59 | 34
Mark | 45 | Basic Character Customization | Done | 6 | 10 | bar: 1 to 10
| 46 | Expand Character Customiza on (Track Combat Stat, etc.) | In Progress | 6 | bar: 11
| 47 | Enable Basic Character Progression (Gaining XP, etc.) | In Progress | 16 | bar: 12
| 48 | Expand Character Progression (Track Power-Ups, etc.) | In Progress | 6 | bar: 13
| 49 | Implement NPC tracking | In Progress | 10 | bar: 14
| 50 | Finalize Special Cases (Respawning when Health == 0, etc.) | In Progress | 6 | bar: 15
| 51 | Finalize Tracking Stats | Planned | 6
| 52 | Testing | Planned | 2
| 53 | Total |  | 58 | 10
Shan | 54 | Requirements Collection | Done | 3 | 4 | bar: 1 to 4
| 55 | Program Initial Inventory System and subclasses | Planned | 8
| 56 | Make sprites for items | In Progress | 7 | 1 | bar: 5
| 57 | Program effects for Power-Ups + PoisonApple | In Progress | 3 | 1 | bar: 6
| 58 | Program all Item reactions to Player collision – item description text placeholder, Use Now vs. Store for Later | In Progress | 2 | 1 | bar: 7
| 59 | Program how/when Inventory is displayed | Planned | 1
| 60 | Program placeholder for text shown when item is selected in Inventory | Planned | 2
| 61 | Program functionality of adding items to Inventory + notification to Player | Planned | 4
| 62 | Program effect of Player trying to add too many items to Inventory excluding Collectibles | Planned | 1
| 63 | Program automatic addition to Inventory for Collectibles with message (even if Inventory is full) | Planned | 2
| 64 | Program increase in Inventory slots when clueCount increases | Planned | 4
| 65 | Program result of Player clicking Use Now on Golden Apple (depends on health) and Player Clicking Store Later | Planned | 2
| 66 | Program result of Player clicking Use Now and Player clicking Store Later on all other powerups | Planned | 3
| 67 | Program disappearance of Items when used/discarded/read (in case of SecretScroll) | Planned | 1
| 68 | Program result of Player clicking Use on Golden Apple in Inventory (depends on health) | Planned | 1
| 69 | Program OwlsWing effect when Player clicks Use (both talking to and not talking to Cat) | Planned | 2
| 70 | Program CanOfTuna effect when Player clicks Use (both talking to and not talking to Cat) | Planned | 2
| 71 | Testing | Planned | 10
| 72 | Total |  | 58 | 7
Liz | 73 | Requirements | Done | 5 | 3 | bar: 1 to 3
| 74 | Creating Visual Main Menu Screen | Done | 3 | 5 | bar: 4 to 8
| 75 | Coding Main Menu behavior scripts | Done | 2 | 4 | bar: 9 to 12
| 76 | Creating Pause menu Screen | In Progress | 2 | 5 | bar: 13 to 17
| 77 | Coding Pause menu behavior and scripts | Done | 3 | 2 | bar: 18 to 19
| 78 | Creating inventory button and menu | Planned | 2
| 79 | Coding Inventory button and behavior script | Planned | 3
| 80 | Designing Victory Screen | Planned | 1
| 81 | Coding Victory Screen behavior scripts | Planned | 3
| 82 | Designing Game Over Screen | Planned | 1
| 83 | Coding Game Over screen behavior scripts | Planned | 3
| 84 | Testing | Planned | 4
| 85 | Total |  | 32 | 19
Hengyi | 86 | Requirements Collection | Done | 5 | 3 | bar: 1 to 4
| 87 | Environment elements design and audio collection | Done | 5 | 5 | bar: 5 to 9
| 88 | Environment Manager Design | In Progress | 6 | 2 | bar: 9 to 10
| 89 | Audio Manager Design | In Progress | 5 | 2 | bar: 11 to 12
| 90 | Scene Engine Implementation | In Progress | 10 | 3 | bar: 13 to 15
| 91 | Weather Implementation | Planned | 2
| 92 | Tiles Implementation | Planned | 2
| 93 | Background Implementation | In Progress | 2 | 2 | bar: 16 to 17
| 94 | Background Music Implementation | In Progress | 2 | 2 | bar: 18 to 19
| 95 | Sound Effect Implementation | In Progress | 2 | 2 | bar: 20 to 21
| 96 | Testing and Optimization | Planned | 5
| 97 | Final Integration | Planned | 5
| 98 | Total |  | 51 | 21
99
100
101
102
103
104
105
106
107
108
109
110

## SA
Systems Analysis Chart
|  | Task | Status | Predicted (hrs) | Time Spent (hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
Bidhan | 1 | Install Unity | Done | 1 | 2 | bar: 1 to 2
| 2 | Class Diagram | Done | 3 | 6 | bar: 3 to 8
| 3 | Champion | Done | 2 | 4 | bar: 9 to 12
| 4 | Sequence Diagram | Done | 1 | 1 | bar: 13
| 5 | Total |  | 7 | 13
Todd | 6 | Install Unity | Done | 1 | 1 | bar: 1
| 7 | Make Version 1.0 of RFP | Done | 1 | 1 | bar: 2
| 8 | Update RFP to Version 2.0 | Done | 1 | 1 | bar: 3
| 9 | Champion | Done | 8 | 15 | bar: 4 to 18
| 10 | Class Diagram | Done | 2 | 3 | bar: 19 to 21
| 11 | Diagram 0 | Done | 4 | 5 | bar: 22 to 26
| 12 | Class Diagram v2 | Done | 1 | 2 | bar: 27 to 28
| 13 | Sequence Diagram | Done | 2 | 2 | bar: 29 to 30
| 14 | Total |  | 20 | 30
Alex | 15 | Install Unity | Done | 1 | 2 | bar: 1 to 2
| 16 | Update RFP to Version 3.0 | Done | 1 | 2 | bar: 3 to 4
| 17 | Class Diagram | Done | 6 | 5 | bar: 5 to 9
| 18 | Champion | Done | 5 | 10 | bar: 10 to 19
| 19 | Sequence Diagram | Done | 2 | 2 | bar: 20 to 21
| 20 | Total |  | 15 | 21
Mark | 21 | Install Unity | Done | 1 | 2 | bar: 1 to 2
| 22 | Class Diagram v1 | Done | 3 | 1 | bar: 3
| 23 | Class Diagram v2 | In Progress | 1
| 24 | Champion v1 | Done | 5 | 10 | bar: 4 to 13
| 25 | Champion v2 | In Progress | 1
| 26 | Sequence Diagram | Done | 2 | 1 | bar: 14
| 27 | Total |  | 13 | 14
Shan | 28 | Install Unity | Done | 2 | 2 | bar: 1 to 2
| 29 | Class Diagram v1 | Done | 3 | 3 | bar: 4 to 6
| 30 | Update RFP | Done | 2 | 1 | bar: 7
| 31 | Champion | Done | 7 | 13 | bar: 8 to 20
| 32 | Class Diagram v2 | Done | 1 | 4 | bar: 21 to 24
| 33 | Sequence Diagram | Done | 1 | 1 | bar: 25
| 34 | Create Schedule Charts | Done | 2 | 5 | bar: 3; 26 to 29
| 35 | Total |  | 18 | 29
Liz | 36 | Install Unity | Done | 1 | 2 | bar: 1 to 2
| 37 | Update RFP to Version 5.0 | Done | 2 | 1 | bar: 3
| 38 | Class Diagram | Done | 3 | 10 | bar: 4 to 13
| 39 | Champion | Done | 2 | 6 | bar: 14 to 19
| 40 | Sequence Diagram | Done | 1 | 4 | bar: 20 to 23
| 41 | Total |  | 9 | 23
Hengyi | 42 | Install Unity | Done | 1 | 2 | bar: 1 to 2
| 43 | Update RFP to Version 4.0 | Done | 2 | 3 | bar: 3 to 5
| 44 | Class Diagram v1 | Done | 1 | 2 | bar: 6 to 7
| 45 | Class Diagram v2 | Done | 2 | 2 | bar: 8 to 9
| 46 | Champion | Done | 10 | 16 | bar: 10 to 25
| 47 | Sequence Diagram | Done | 2 | 2 | bar: 26 to 27
| 48 | Total |  | 18 | 27
49
50
51
52
53
54
55

## Meetings
Team Meetings
| Date | 2025-02-05 | 2025-02-07 | 2025-02-12 | 2025-02-14 | 2025-02-17 | 2025-02-19
|  | Diagram 0 and Champion Discussion | Class Diagram Reviewing w/BC | SA Presentation Planning | Champion and Storyboard Reviewing w/BC | SA Pres Review w/BC | MVP Discussion
| Hours | 2 | 3 | 2 | 2 | 1 | 2
Bidhan | 7 |  | TRUE | TRUE |  |  | TRUE
Todd | 12 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Alex | 11 | TRUE | TRUE | TRUE | TRUE |  | TRUE
Mark | 7 | TRUE |  | TRUE | 1 |  | TRUE
Shan | 11 | TRUE | TRUE | TRUE | TRUE |  | TRUE
Liz | 12 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Hengyi | 10 | TRUE | TRUE | TRUE | 1 |  | TRUE
Total | 70 | 12 | 18 | 14 | 10 | 2 | 14

## Overhead
Overhead
| Bidhan | Todd | Alex | Mark | Shan | Liz | Hengyi
Training | 8 | 8 | 8 | 8 | 8 | 8 | 8
SA Presentation Prep | 5 | 6 | 5 | 7 | 2 | 2 | 8
Software Development Specialists Presentation Prep
Team Lead Presentation Prep |  | 15 | 10 |  | 3
Github Troubleshooting |  |  | 4
Total | 13 | 29 | 27 | 15 | 13 | 10 | 16

## Deliverables
Deliverables
| TL1 Deliverables | TL2 Deliverables | TL3 Deliverables | TL4 Deliverables | TL5 Deliverables | TL6 Deliverables
| Date Due: | Date Due: 2/25 | Date Due: | Date Due: | Date Due: | Date Due:
Have a function that the MVP can call in GIT
Deliverable Tracker
|  | Bidhan | Todd | Alex | Mark | Shan | Liz | Hengyi
TL 1
| TL 2 | ü | ü | ü | ü | ü | ü | ü
TL 3
TL 4
TL 5
TL 6